## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2251-swen-261-07-2
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a user I want to be able to press a button to go back to the main dashboard page from another page. | Given I am a helper when I use the button to go back to the dashboard page then I expect any modification I made while in the basket page to be saved | Pass | TH; 10/16/25; instead of having a specific back button on each page, implemented a permanent 'back to cupboard' button on all pages
As a helper I want to be able to adjust the quantity of a need in my basket if I decide I want more or less. | Given I select a need in my basket when I click on the dropdown box to select the quantity then I expect the basket to update | Pass | TH; 10/16/25;
As an admin I want to be able to edit a need that is already in the cupboard so that they are up to date. | Given I am on the need editor page when I view the page then I expect to see fields related to the need info fields that I can edit. | Pass | JU; 10/16/25;
| Given I am on the need editor page when I view the page then I expect to be able to see and click on a update need button. | Pass | JU; 10/16/25;
| Given I am on the need editor page viewing the different fields when I click on a field then I expect to be able to type or choose select options to change need information | Pass | JU; 10/16/25;
| Given that I am not logged in as an admin when I am viewing the cupboard then I will not see the need editor page | Pass | JU; 10/16/25;
| Given I am on the need editor page when I click on the update need button then I expect to be sent back to the cupboard and the updated need be there | Pass | JU; 10/16/25;
As a user, I want to be able to see a visual representation of the need and the relevant information for that need so I know what needs there are. | Given there are needs in the cupboard when I am on the dashboard then I expect each need to display relevant information on that need. | Pass | TH; 10/16/25;
| Given there are no needs in the cupboard when I am on the dashboard then I expect no needs to display. | Pass | DZ; 10/21/25
As a user, I want to be able to log in to my account | Given that I have not yet signed in when I see the Home page then I must see a means to sign in. (such as a link or button). | Pass | JU; 10/14/25;
| Given that I am on the login page when I enter my username in the login form and click the login button then I expect the system to take me to my dashboard. | Pass | JU; 10/14/25;
| Given that I am on the login page when I login with a non-existent username then I expect the system to reject the login attempt and return to the Login page. | Pass | DZ; 10/21/25
| Given that I clicked create account when I entered a username that already exists, then I expect the system to show an error message | Pass | JU; 10/14/25;
| Given that I am on the login page, when I click 'Create Account' and enter a valid username, I expect the system to create an account. | Pass | JU; 10/14/25;
As a helper I want to be able to click a button so I can access the items I’ve added to my basket. | Given I click the view basket button when I am logged in as a helper then display my current basket. | Pass | DZ; 10/19/25;
| Given that I am not a helper when I am on the cupboard page then I can not see the basket button or access the button | Pass | JU; 10/16/25;
As an admin I want to be to able to acess a page to edit the needs. | Given the need exists when I see a need in the cupboard then I expect to be able to see an edit button. | Pass | JU; 10/14/25;
| Given the need exists when I click on the edit button then I expect to be taken to that need's edit page | Pass | JU; 10/14/25;
As a user, I want to be able to search for needs within a cupboard via a search bar, so that I can find the needs I am looking for. | Given there are needs in the cupboard whose name contains all or part of a text I am looking for when I type all or part of the text in the search bar then I expect those needs whose names contain that text to appear in a list. | Pass | TH; 10/16/25;
| Given there are no needs in the cupboard whose name contains all or part of a text I am looking for when I type all or part of the text in the search bar then I expect no needs to appear in a list. | Pass | TH; 10/16/25;
As a helper I want to be able to select an amount of a need and add it to my basket so that I can fund it. | Given that I am a helper When I want to add more than 1 of a need to my basket Then I can select a different amount from the drop down | Pass | TH; 10/16/25;
| Given that I am a helper and I am adding more than one of a need to my basket When I select the drop down, then I can select between 1 and max amount remaining | Pass | JU; 10/20/25;
| Given that I am a helper and there is an amount selected When I hit the add to basket button it Then it adds the amount to my basket | Pass | TH; 10/16/25;
As a helper I want to be able to checkout with my basket of needs so I can fund them. | Given that I am a helper when I am on the basket page viewing my basket then I expect to see a button to checkout with | Pass | DZ; 10/19/25;
| Given that I am a helper when I have no needs in my basket then I expect the checkout button to not do anything at the moment | Pass | JU; 10/22/25; originally let you check out with an empty basket, fixed
| Given that I am a helper when I have needs in my basket then I expect the checkout button to check me out when I press it | Pass | DZ; 10/19/25;
As a helper I want to be able to see a visual representation of the needs in my basket so I can remember what is in my basket. | Given that I am a helper when I have needs in my basket then I expect to see each of them listed in my basket | Pass | DZ; 10/19/25;
| Given that I am a helper when I have no needs in my basket then I expect to see nothing in my basket | Pass | DZ; 10/19/25;
As an admin I want to be to able to delete needs so only relevant ones are still shown. | Given I click the delete need button when I am logged in as an admin then display a confirmation. | Pass | JU; 10/16/25;
As a user I want to be able to logout of the system after I am done with everything I am doing. | Given I click the logout button when I am logged in as a user then log me out and display a confirmation message. | Pass | AL; 10/21/25
As an admin I want to be to able to create a need so that new needs can be added to the cupboard. | Given I click the create need button **when** I am logged in as an admin then sends me back to the login page | Pass | JU; 10/16/25;
| Given that I am not logged in as an admin when I view the cupboard then I will not see the create need button | Pass | JU; 10/16/25;
| Given I am on the need creator page when I click on the create button then a new need shall be saved with the info I have set it as. | Pass | JU; 10/16/25;
As a helper I want to be able to remove a need from my basket so that I don’t get stuck with a need I don’t want. | Given that I am a helper when I have a need in my basket then I expect to see a button that lets me remove that need from the basket | Pass | DZ; 10/19/25;
| Given that I am a helper when I remove the whole quantity from basket button then I expect that item to no longer be in my basket | Pass | DZ; 10/19/25;
As an Admin I want to view visual graph summarizing need information so that I can monitor the status' of needs currently available. | **GIVEN** there are needs **WHEN** I view the need metrics summary **THEN** I should see a visual representation of the metrics provided | Pass | MT; 11/10
As an Admin I want to view a visual graph summarizing helper information so that I can monitor the status' of helpers and their contributions. | **GIVEN** there are registered helpers **WHEN** I view the helper metrics summary **THEN** I should see a visual representation of the metrics provided | Pass | MT; 11/10
As an Admin I want to view a list summarizing need information so that I can monitor the status' of needs currently available. | **GIVEN** there are listed needs in the cupboard **WHEN** I view the need metrics summary **THEN** I should see the number of currently listed needs. | Pass | MT; 11/10
| **GIVEN** there are unlisted needs in the cupboard **WHEN** I view the need metrics summary **THEN** I should see the number of currently unlisted needs. | Pass | MT; 11/10
| **GIVEN** there are listed volunteer needs in the cupboard **WHEN** I view the need metrics summary **THEN** I should see the number of currently listed volunteer needs. | Pass | MT; 11/08
| **GIVEN** there are monetary listed needs in the cupboard **WHEN** I view the need metrics summary **THEN** I should see the number of currently listed monetary needs. | Pass | MT; 11/08
| **GIVEN** there are listed resource needs in the cupboard **WHEN** I view the need metrics summary **THEN** I should see the number of currently listed resource needs. | Pass | MT; 11/08
| **GIVEN** there are listed needs in the cupboard **WHEN** I view the need metrics summary **THEN** I should see the number of fulfilled needs. | Pass | MT; 11/10
| **GIVEN** there are listed needs in the cupboard **WHEN** I view the need metrics summary **THEN** I should see the number of unfulfilled needs. | Pass | MT; 11/10
As an Admin I want to view a list summarizing helper information so that I can monitor the status' of helpers and their contributions. | **GIVEN** there are registered helpers **WHEN** I view the helper metrics summary **THEN** I should see the number of currently registered helpers | Pass | MT; 11/10
| **GIVEN** there are no registered helpers **WHEN** I view the helper metrics summary **THEN** all the fields should be 0 | Pass | MT; 11/10
| **GIVEN** there are registered helpers **WHEN** I view the helper metrics summary **THEN** I should see the helper who has made the most contributions | Pass | MT; 11/09
| **GIVEN** there are registered helpers **WHEN** I view the helper metrics summary **THEN** I should see the number of helpers that currently have needs in their basket | Pass | MT; 11/10
As an admin I want to be able to see chat box on the admin page so that I can communicate with all other admins. | **Given** I am logged in as admin **when** I look at the admin page **then** I expect to see an admin chat section. | Pass | AL; 11/09
| **Given** I am on the admin page logged in as admin **when** I view the admin chat **then** I expect to see a textbox to type and send my message. | Pass | AL; 11/09
| **Given** I am on the admin page logged in as admin **when** I view the admin chat **then** I expect to see a send button to send whatever I typed in the message box. | Pass | AL; 11/09
| **Given** I am on the admin page **when** I look messages box **then** I expect to see a scrollable list of my messages and other admin messages ordered by sent timestamp. | Pass | AL; 11/09
As a helper I only want to see needs that still need to be fulfilled in my cupboard view. | **Given** I am a helper **when** I am looking at the cupboard **then** I expect to only see needs that I could add to my basket | Pass | TH; 11/07
| **Given** I am helper **when** I check out the full quantity of a given need **then** it will no longer be visible to me or any other helpers in the cupboard | Pass | TH; 11/07
As an admin, I want to be able to delist needs so that helpers temporarily can’t interact with them. | **Given** I am an admin **when** I am viewing the cupboard **then** I should see an object to delist a unfulfilled need | Pass | TH; 11/05
| **Given** I am an admin **when** an unfulfilled need is currently delisted **then** I should have the option to relist it | Pass | TH; 11/05
| **Given** I am an admin **when** if I need to edit a delisted need **then** I should be able to | Pass | TH; 11/05
As a Super Admin, I want to be able to create admins so that they can help manage the system. | **GIVEN** I am on the "create admin" page **WHEN** I fill out the information and click "create" **THEN** I expect a new admin to be added to the system. | Pass | AL; 11/07
| **GIVEN** I am on the "create admin" page **WHEN** I fill out the form with invalid information **THEN** I expect to be prompted of the error with no new admin created. | Pass | AL; 11/07
As a user, I want my account to be password protected so that other users can’t access it. | **Given** I know the username and password for my account **when** I enter them both correctly **then** I expect to be able to login to my account | Pass | JU; 11/08
| **Given** I know the username but input the password wrong **when** I try to login **then** the system will let me know that my username or password was entered incorrectly | Pass | TH; 11/08
| **Given** I know the password but input the username wrong **when** I try to login **then** the system will let me know that my username or password was entered incorrectly | Pass | JU; 11/08
As an admin I want to send messages to other admins so that all admins can be kept up to date on important info. | **Given** I have typed something in the message box **when** I click the send button **then** I expect my message to be sent to other admins and appear on the message chat box section. | Pass | AL; 11/11; Was moved into a different component and broke temporarily
| **Given** I am a different admin logged in **when** another admin sends a message to the chat **then** I expect to see the message they sent at the time they sent it. | Pass | AL; 11/11;
As a user I want to be greet by a NO SPOILERS 404 page not found when I go off course | **Given** I am trying to access the system by url manipulation **when** I type in an invalid url **then** I expect a 404 page with a cat gif | Pass | TH; 11/04
| **Given** I am on the 404 page **when** I realize my mistake **then** there will be a button to take me back to the cupboard | Pass | TH; 11/04